## Slide 1: Novartis Data DevOps Platform Engagement Executive Summary
4th Oct 2019

## Slide 2: S1 Executive Summary
Novartis DevOps Platform Engagement kick-off started with Altimetrik Engineering teams building tool-chain foundational services on Altimetrik AWS infrastructure.
Agenda:
Program Status Update
RIDAC [Risks/Issues/Decisions/Actions/Changes] areas that require executive or stakeholder review
Scrum Activities Progress Details
  Sprint 1 Objectives Overview and Deliverables
  Demo of Sprint 1 Adoption Scrum Stories
  Sprint 2 Planned Deliverables
2019 - 2020
Sep Oct Nov Dec Jan Feb Mar
Requirements Workshops with F1, EDM, DP/AA, API Gateway, Visualization
July 2019
Adoption Scrum 1
Discovery Scrum
Discovery Scrum AA - Target State
Discovery Scrum API Gateway - Target State
Discovery Scrum Visualization - Target State
Setup and Automation of Provisioning, Configuration and Infrastructure, Accelerator Development for Data Platform Integration
Platform Onboarding Project 1 & Sign off
Discovery Scrum - Documentation
Discovery Scrum – Formulate and Execute Trainings
Onboarding and Tool Chain Prototyping
Setup and Automation of Provisioning, Configuration and Infrastructure, Accelerator Development for Data Platform Integration
Platform Onboarding Project 2 & Sign off
Onboarding and Product backlog review
Adoption Scrum 2
S1

## Slide 3
Program Status
Novartis Discovery and Adoption teams assembled, and initial SPOC session completed with Novartis engineering teams.
Primary goals for Sprint 1 was building foundational services, identify selection of proposed tool chain, and construct the internal engagement model (across Discovery / Adoption team).
  Installation and configuration of Jira, Jenkins, Bitbucket and SonarQube
  Complete first level integration of Jira, Jenkins and Bitbucket
  Installation of Bitbucket plugins
Approach for implementation is 2-phased with initial phase of tool chain developed on Altimetrik AWS account and phase 2 will require automated setup/migration of tool chain from Altimetrik AWS to Novartis AWS account.
MSA and SOW Approval/Sign off in progress [Need to accelerate to help unblock onboarding team to Novartis system]
Program Summary
Open Items | Risks
Yellow
October 4, 2019
Program Status
Date
Date | Risk / Open Item | Action | Owner
9/18 | MSA and SOW approval/ sign-off in progress | MSA / SOW Sign-Off | Novartis
Date | Risk / Open Item | Owner
9/25 | Onboarding Process/Documentation and Requirements [ Corp / Network ID, Assets, and Network related process] | Jyothi Sai
9/25 | Onboarding Resource Information | Vijay Sampath
9/25 | Consultant Workspace setup process and policy documents | Jyothi Sai
Actionable Items

## Slide 4
Adoption Scrum Summary
Walk-thru of approach, team structure, engagement touch points, and tool set proposal [Jira, (Bitbucket / Gitlab), Jenkins, SonarQube, Ansible, Artifactory, Prometheus, Grafana, ELK)].
Evaluation of 3 source systems (Gitlab EE, Gitlab Community, and Atlassian BitBucket)
Setup and configuration of foundational services (AWS Route 53, IAM, EC2, ECS, Security Groups) to stand up proposed tool chain and apply configuration of tools, and import necessary plugins, and integration points.
Configuration setup consist of Jira project workflows / screens and issue types, Bitbucket branching model, Jira/Jenkin/SonarQube plugins, and sample code setup for Python, Scala and R.
  Installation and configuration of Jira, Jenkins, Bitbucket and SonarQube
  Complete first level integration of Jira, Jenkins and Bitbucket
  Installation of Bitbucket plugins
Sprint 1 Deliverables Summary
Open Items | Risks
Date | Risk / Open Item | Action | Owner
9/18 | Discovery Scrum deep-dive sessions with EDM delayed due to lack of signed SOW | Expedite Onboarding Process or provide exception to engage Novartis SPOC | Novartis
Continuous workflow design and implementation
  Standard branching convention, auto transition of Jira issue types by source code control actions.
  Standardizing versioning strategy for R, Scala and Python applications.
  Configure automatic triggers within Jenkins to build and give fast feedback to the developer upon each git commit or git push with multi-branch support.
Define skeleton stages for Jenkinsfile (build, test, package and publish).
Provide quality gates with detail information to enforce rules based on Jenkins build and Sonar build status.
Evaluation of Gitlab integration with tool chain for both community and enterprise edition.
Evaluation of ephemeral Jenkins build slaves.
Sprint 2 Scope Details

## Slide 5: Thank You…